## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Set up the complete project development environment, including the installation and configuration of JDK, IntelliJ IDEA, GitHub, and MySQL. Ensured all tools were properly integrated, verified system configurations, and successfully completed the initial Git repository setup for version control and collaboration. | MUST HAVE | None | Shubham Badgujar | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Implemented the Product model and InventoryManager classes using Object-Oriented Programming (OOP) principles to ensure modularity and code reusability. Integrated robust exception handling mechanisms for smooth error management. Additionally, installed and configured MySQL Workbench to efficiently store, manage, and visualize the project’s database records. | MUST HAVE | US-1 | Shubham Badgujar | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Developed and implemented the persistence layer using CSV files to manage initial data storage, retrieval, and backup operations. This setup ensured smooth data handling before database integration, enabling reliable data access, easy debugging, and secure backup management for the project. | MUST HAVE | US-2 | Shubham Badgujar | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Established a JDBC connection between the Java application and the MySQL database to enable seamless communication and data manipulation. Verified the successful execution of SQL CRUD (Create, Read, Update, Delete) operations through MySQL Workbench, ensuring proper data integration, consistency, and reliability within the system. | MUST HAVE | US-3 | Shubham Badgujar | 3- Completed
Sprint 1 | Sprint 1 | US-5 | Implemented the ProductDAO interface and its corresponding DAOImpl class to define and execute CRUD (Create, Read, Update, Delete) operations for product data management. Ensured clean separation between the data access layer and business logic, promoting scalability, maintainability, and efficient interaction with the database. | MUST HAVE | US-4 | Shubham Badgujar | 3- Completed
Sprint 1 | Sprint 1 | US-6 | Integrated the JDBC-based CRUD methods with a console-based user interface, allowing users to interactively perform database operations such as adding, viewing, updating, and deleting product records. This integration enabled real-time communication between the console and the database through JDBC connectivity, ensuring smooth and dynamic data management within the system. | MUST HAVE | US-5 | Shubham Badgujar | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Implemented the Read functionalities including GetAll and GetByID methods to retrieve complete product lists or specific product details from the database. Integrated these operations into the console interface for administrators, enabling efficient data viewing, management, and verification directly through interactive console commands. | MUST HAVE | US-6 | Shubham Badgujar | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Implemented the Update and Delete functionalities to modify and remove product records from the database. Incorporated robust input validation to ensure data integrity, prevent invalid operations, and maintain consistency across the system during record updates and deletions. | MUST HAVE | US-7 | Shubham Badgujar | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Integrated all CRUD (Create, Read, Update, Delete) functionalities into a comprehensive console menu, enabling a seamless and interactive workflow for users. This setup provided a structured navigation system, allowing users to perform complete product management operations efficiently through a single unified interface. | MUST HAVE | US-8 | Shubham Badgujar | 3- Completed
Sprint 2 | Sprint 2 | US-10 | Added comprehensive input validation mechanisms to ensure accurate and reliable user data entry during CRUD operations. Implemented detailed exception handling to capture, manage, and display meaningful error messages, preventing system crashes and ensuring smooth, user-friendly interaction throughout the application. | MUST HAVE | US-9 | Shubham Badgujar | 3- Completed
Sprint 2 | Sprint 2 | US-11 | Implemented JUnit test cases for both the DAO and utility layers to thoroughly verify data handling logic and ensure system reliability. These tests validated CRUD operations, data consistency, and utility methods, helping identify potential issues early and maintaining the overall integrity and robustness of the application. | MUST HAVE | US-10 | Shubham Badgujar | 3- Completed
Sprint 2 | Sprint 2 | US-12 | Developed and implemented a CSVHelper utility to facilitate data export and synchronization between the CSV files and the MySQL database. This feature enabled seamless data backup, import/export operations, and ensured data consistency across both storage systems for efficient data management and recovery. | MUST HAVE | US-11 | Shubham Badgujar | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Developed an EmailService module leveraging the JavaMail API (SMTP) to automatically send reports, notifications, and alerts to users and administrators. Configured secure email authentication and delivery settings to ensure reliable communication, enabling automated report sharing and timely system alerts for better monitoring and management. | MUST HAVE | US-12 | Shubham Badgujar | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Integrated the EmailService module into the application’s admin menu, allowing administrators to directly send product reports via email from within the system. This integration streamlined report distribution, enabling quick sharing of inventory updates and analytics through automated, secure email delivery. | MUST HAVE | US-13 | Shubham Badgujar | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Integrated the database, CSV, and email modules to create a unified and automated reporting workflow. Enabled seamless data synchronization, report generation, and email delivery within a single streamlined process. | SHOULD HAVE | US-14 | Shubham Badgujar | 3- Completed
Sprint 3 | Sprint 3 | US-16 | Implemented an OTP-based email verification service to enhance security during user registration. The system generates and sends a one-time password (OTP) to the user’s registered email, allowing account activation only after successful verification. | COULD HAVE | US-13 | Shubham Badgujar | 3- Completed
Sprint 3 | Sprint 3 | US-17 | Added “Verify Email” and “Resend OTP” functionalities to the registration menu, enabling users to confirm their email addresses securely and request a new OTP if needed. This ensures reliable verification and smooth user onboarding. | MUST HAVE | US-16 | Shubham Badgujar | 3- Completed
Sprint 3 | Sprint 3 | US-18 | Enhanced the user registration and login flow by integrating OTP-based email validation and secure password hashing. This improvement strengthens account security, ensures verified user access, and protects sensitive credentials from unauthorized use. | MUST HAVE | US-16 | Shubham Badgujar | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Implemented a Stock Alert Service to continuously monitor product quantities and trigger threshold-based low stock alerts. This ensures proactive inventory management by notifying administrators when stock levels fall below the defined limit. | MUST HAVE | US-18 | Shubham Badgujar | 3- Completed
Sprint 4 | Sprint 4 | US-20 | Developed a scheduled alert generator to automate recurring stock monitoring at predefined intervals. This feature ensures timely detection of low inventory levels and consistent alert notifications without manual intervention. | MUST HAVE | US-19 | Shubham Badgujar | 3- Completed
Sprint 4 | Sprint 4 | US-21 | Integrated email notification functionality for stock alerts into the main menu, enabling automatic email updates to administrators when product quantities drop below threshold levels. This ensures real-time awareness and efficient inventory management. | MUST HAVE | US-19 | Shubham Badgujar | 3- Completed
Sprint 4 | Sprint 4 | US-22 | Added an advanced search functionality allowing both admin and user roles to find products by name, category, or ID. This feature enhances accessibility and improves efficiency in navigating and managing product records. | MUST HAVE | US-9 | Shubham Badgujar | 3- Completed
Sprint 4 | Sprint 4 | US-23 | Conducted comprehensive end-to-end testing covering user registration, OTP verification, email notifications, and stock alert functionalities. Ensured seamless integration, accuracy, and reliability across all modules for a smooth and secure user experience. | MUST HAVE | US-18 | Shubham Badgujar | 3- Completed
Sprint 4 | Sprint 4 | US-24 | Packaged, finalized, and deployed the complete Inventory Management System with all integrated modules, including authentication, email services, and stock alerts. Ensured a stable, production-ready build with verified functionality and optimized performance. | MUST HAVE | US-23 | Shubham Badgujar | 3- Completed
Note on F1: ====== ID#AAABqnR-1bo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.